# Social Generative Interfaces as Co-Designers

Independent Study Proposal  ·  CASA, Generative UI, and Agentic Interaction

Student: ____________________   ·   Faculty supervisor: Professor José Sánchez   ·   Fall 2026   ·   Target: mid-December   ·   Testbed: EVA

# Project premise

- Investigate how CASA (Computers Are Social Actors) changes when the social actor is not only a voice or character, but a voice-enabled agent and its dynamically generated workspace acting as one entity.

- Use EVA to study a system that listens, displays affective behavior, retrieves remembered preferences, and constructs or revises task-specific interfaces in real time.

- Treat EVA's apparent emotion as bounded computational affect expressed through voice, language, timing, memory, motion, and eye behavior; the study examines human interpretation rather than claiming machine sentience.

- Connect three design layers:

  - Relational: voice, social eye, affect, personality, turn-taking, and shared history.

  - Generative: constrained components, layouts, semantic revisions, and temporal continuity.

  - Constitutional: provenance, reversible interaction, inspectable memory, deterministic permissions, and safety-owned controls.

- Extend Sánchez's research on generative interfaces, combinatorial systems, and player design agency into human-AI co-design.

# Primary research question

- How does embodying a constrained generative UI system as a voice-enabled, emotionally expressive social co-designer, rather than an instrumental generator, affect users' perceived shared authorship during iterative dashboard creation?

# Supporting questions

- What component, layout, and revision rules let EVA conversationally extend an interface without disrupting visual or interaction continuity?

- How do voice, eye behavior, remembered preferences, conversational timing, and affect make EVA and its workspace appear to be one social actor?

- How can social expression coexist with calibrated reliance, inspectable provenance, user control, and safety boundaries?

# Intended contributions

- A CASA-informed design framework for generative interfaces that operate as social co-designers.

- A constrained generative UI grammar for task-specific, conversationally revised dashboards.

- An agentic interaction model supporting voice, semantic direct manipulation, memory, interruption, and reversible revisions.

- A trust-and-safety model separating expressive generated UI from deterministic authority and safety-owned controls.

- Empirical evidence about shared authorship, trust and reliance, personality or intent attribution, and task support.

# Prototype and conditions

- Build two mocked workflows using the same component grammar:

  - a seven-day weather dashboard that can add wind, comparison, or detail layers;

  - a calendar-planning dashboard that can reorganize commitments and priorities.

- Demonstrate the interaction loop: voice activation, social eye, visible generation, initial dashboard, conversational revision, real-time interface patch, and explicit conversational closure.

- Visualize retrieval across inspectable memory regions: episodic, semantic, preference, relational, affective, identity, and procedural memory.

- Compare two functionally equivalent conditions:

  - Relational co-designer: affective voice delivery, social eye behavior, collaborative language, interpreted-intent explanations, and references to shared memory.

  - Instrumental generator: the same voice identity, data, capabilities, memory, grammar, and response timing, but functional language, nonsocial status behavior, and silent preference application.

- Treat relational framing as one bundled condition. The study will not claim to isolate the individual effects of voice, sarcasm, eye behavior, memory, or affect.

- Retain restrained sarcasm as part of the relational prototype while flagging cultural and linguistic variability; later study materials will consider literal wit, warm understatement, adjustable sarcasm, and non-ironic alternatives.

# Study design and measures

- Plan a counterbalanced within-subject comparison using the weather and planning tasks; finalize recruitment and sample size with faculty and institutional human-subject guidance.

- Hold functionality, generated results, voice identity, timing, visual grammar, and memory capability constant across conditions.

- Primary outcome: perceived shared authorship and co-agency over the resulting interface.

- Secondary outcomes: perceived control, task success, trust and reliance, personality or intent attribution, willingness to accept revisions, and correction behavior.

- Collect post-condition scales, interaction logs, generated-artifact comparisons, and semi-structured interview responses.

- Use synthetic data and no production account access or consequential device actions.

- Obtain required institutional approval before recruitment; if timing delays recruitment, complete a faculty-reviewed pilot and submission-ready study protocol without weakening the prototype deliverable.

# Trust-and-safety requirements

- Generate validated declarative UI data rather than executable model-generated code.

- Apply identical deterministic safety policy to both experimental conditions.

- Keep provenance, uncertainty, memory use, and revision history inspectable.

- Prevent personality, eye behavior, or generated cards from imitating or weakening safety-owned confirmation surfaces.

- Treat silence as no further request, never as approval or satisfaction.

- Allow users to interrupt, reject, correct, rewind, or dismiss EVA without emotional pressure or loss of control.

- Prohibit sarcasm during uncertainty, failure, privacy, distress, confirmation, or security events.

# Semester curriculum

- Weeks 1-2: CASA, affective computing, mixed-initiative interaction, generative design, agentic UI, and trust literature; finalize constructs and protocol.

- Weeks 3-4: Define the three-layer framework, component ontology, UI schema, affect rules, memory regions, and safety invariants.

- Weeks 5-7: Implement weather and calendar workflows, voice and eye behavior, progressive generation, semantic revision, and simulated memory.

- Week 8: Integrate both research conditions; conduct faculty and lab critique.

- Week 9: Pilot the tasks, instruments, logs, and interview guide; freeze the study protocol and complete required ethics steps.

- Weeks 10-11: Conduct the participant study, subject to approval, while maintaining anonymized research records.

- Week 12: Analyze quantitative, behavioral, artifact, and interview evidence; document limitations and counterevidence.

- Weeks 13-14: Finalize the design framework, constrained grammar, prototype, conference-style manuscript, recorded demonstration, and presentation.

# Deliverables

- Annotated bibliography, precedent matrix, research protocol, and study instruments.

- GENERATIVE_UI_DESIGN.md: framework, grammar, components, affect, memory, motion, trust states, safety rules, and anti-patterns.

- Versioned declarative UI schema, mocked datasets, and interactive two-task EVA prototype.

- Participant-study results with anonymized data, analysis materials, limitations, and design recommendations, subject to institutional policy.

- Conference-style manuscript prepared for later revision and potential submission to CHI or another appropriate HCI venue; acceptance or deadline alignment is not assumed.

- Portfolio-ready recorded demonstration, final presentation, and concise resume project description.

# Assessment proposal

- 15% research foundation and precedent synthesis.

- 20% CASA-informed framework and constrained UI grammar.

- 25% iterative prototypes and integrated two-task system.

- 20% participant-study design, execution, and analysis.

- 15% conference-style manuscript and critical reflection.

- 5% final presentation and recorded demonstration.

# Scope and interpretation

- Focus on the research surface of EVA's planning document; full backend completion, production connectors, unrestricted device control, and Live2D integration remain outside the semester scope.

- Do not claim that EVA experiences subjective emotion; study how users interpret and respond to computational affect.

- Do not generalize the bundled relational comparison into causal claims about individual personality cues.

- Treat personal-use personality preferences as product configuration, not research evidence.

- Present the resulting framework as provisional beyond the tested weather and planning workflows.

# Initial references

- CASA: Nass, Steuer, and Tauber, Computers Are Social Actors, CHI 1994; Nass and Moon, Machines and Mindlessness, 2000.

- Affect and mixed initiative: Picard, Affective Computing, 2000; Horvitz, Principles of Mixed-Initiative User Interfaces, CHI 1999; Amershi et al., Guidelines for Human-AI Interaction, CHI 2019.

- Generative design: Sánchez, Temporal and Spatial Combinatorics in Games for Design, ACADIA 2015.